## Software Engineering Gantt
Title | Assigned to | Start date | End date | Slack | Duration (in days) | % Complete
Create event table; title, start day, start time, end day, end time | Mohan | 2019-09-09 | 2019-09-09 | 0 | 1 | 100
Add title of month to calendar | Kirsten | 2019-09-09 | 2019-10-07 | 7 | 21 | 100
Show next month on Calendar | Kirsten | 2019-09-09 | 2019-10-07 | 7 | 21 | 100
Show prev month on Calendar | Kirsten | 2019-09-09 | 2019-10-07 | 7 | 21 | 100
Fill dates on Calendar | Kirsten | 2019-09-09 | 2019-10-02 | 6 | 18 | 100
Index.html shell calendar | Kirsten | 2019-09-09 | 2019-10-02 | 6 | 18 | 100
Create file to store sign in for server | Ate-jah | 2019-09-09 | 2019-09-09 | 0 | 1 | 100
Create mysql database | Mohan | 2019-09-09 | 2019-09-09 | 0 | 1 | 100
Configuration managment plan 1.0 | Kirsten | 2019-09-16 | 2019-10-07 | 5 | 16 | 100
Team organization Diagram 1.0 | Kirsten | 2019-09-16 | 2019-10-07 | 5 | 16 | 100
Risk management plan 1.0 | James | 2019-09-16 | 2019-10-07 | 5 | 16 | 100
Installation/Maintenance plan 1.0 | Kirsten | 2019-09-16 | 2019-10-07 | 5 | 16 | 100
SDP 1.0 | Everyone | 2019-09-16 | 2019-10-07 | 5 | 16 | 100
Gantt Chart 1.0 | Kirsten | 2019-10-07 | 2019-10-07 | 0 | 1 | 100
Add arrow buttons to navigate month | Kirsten | 2019-10-07 | 2019-10-12 | 2 | 5 | 100
Add button to switch display | Kirsten | 2019-10-07 | 2019-10-12 | 2 | 5 | 100
Add button to go to form | Kirsten | 2019-10-07 | 2019-10-12 | 2 | 5 | 100
Add toolbar | Kirsten | 2019-10-07 | 2019-10-12 | 2 | 5 | 100
Configuration managment plan 1.1 | Kirsten | 2019-10-08 | 2019-10-23 | 4 | 12 | 100
Installation/Maintenance plan 1.1 | Mohan | 2019-10-08 | 2019-10-23 | 4 | 12 | 100
Risk management plan 1.1 | James | 2019-10-08 | 2019-10-23 | 4 | 12 | 100
Gantt Chart 1.1 | Kirsten | 2019-10-08 | 2019-10-23 | 4 | 12 | 100
Installation Guide 1.0 | Kirsten | 2019-10-08 | 2019-11-23 | 10 | 34 | 0
Second Draft SDP 2.0 | Everyone | 2019-10-08 | 2019-10-23 | 4 | 12 | 100
Prototype 1.0 | Everyone | 2019-10-08 | 2019-10-23 | 4 | 12 | 45
SRS 1.0 | Kirsten & Ate-jah | 2019-10-08 | 2019-11-23 | 10 | 34 | 0
SDP 1.1 | Everyone | 2019-10-08 | 2019-11-23 | 10 | 34 | 100
Create php form get_event.php | Kirsten | 2019-10-12 | 2019-10-19 | 2 | 5 | 100
Create php insert_event.php to insert data from to tables | Kirsten | 2019-10-12 | 2019-10-21 | 2 | 6 | 100
Create php delete_event.php to delete the event | Kirsten | 2019-10-19 | 2019-10-26 | 2 | 5 | 100
Gantt Chart 1.2 | Kirsten | 2019-10-23 | 2019-11-18 | 6 | 19 | 100
Use case Diagrams | Ate-jah | 2019-10-23 | 2019-11-18 | 6 | 19 | 100
SDP 1.2 | Everyone | 2019-10-23 | 2019-11-18 | 6 | 19 | 100
Delta Prototype 1.1 | Everyone | 2019-10-23 | 2019-11-18 | 6 | 19 | 40
Validation Proceedure 1.0 | James | 2019-10-23 | 2019-11-18 | 6 | 19 | 0
Component Diagrams | Ate-jah | 2019-10-23 | 2019-11-18 | 6 | 19 | 0
SRS 1.1 | Kirsten | 2019-10-23 | 2019-11-18 | 6 | 19 | 0
Installation Guide 1.1 | Kirsten | 2019-10-23 | 2019-11-18 | 6 | 19 | 0
Create php day.php | Mohan | 2019-10-26 | 2019-11-09 | 3 | 10 | 25
CSS Styling | Everyone | 2019-11-01 | 2019-11-30 | 6 | 21 | 75
Test creating events | Kirsten & Ate-jah | 2019-11-09 | 2019-11-16 | 2 | 5 | 0
Implement necessary changes | Everyone | 2019-11-09 | 2019-11-30 | 5 | 15 | 0
Test deleting events | James & Mohan | 2019-11-16 | 2019-11-23 | 2 | 5 | 0
SRS Final | Everyone | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
Reflection | Everyone | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
Installation Guide Final | Kirsten | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
Gantt Final | Kirsten | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
Validation Proceedure Final | James | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
SDP Final | Everyone | 2019-11-19 | 2019-12-04 | 4 | 12 | 0
Final Prototype | Everyone | 2019-11-19 | 2019-12-02 | 3 | 10 | 0
Test editing events | Kirsten & Ate-jah | 2019-11-23 | 2019-11-30 | 2 | 5 | 0
Implement changes | Everyone | 2019-11-30 | 2019-04-12 | 1 | 4 | 0
Have client test product | Shannon | 2019-11-30 | 2019-04-12 | 1 | 4 | 0